| ATTN: | Date: | 12 Sep 2026 |
| --- | --- | --- |
| ZHANG GANG | Our ref. No.: | SLT-5312-WSN-CVT-0020 |
| Project Manager | Your ref. No.: | N/A |
|  | Answer Required: | Yes |
| China National Chemical Engineering Third Construction Co., Ltd. | Response Date: | 18 Sep 2026 |
|  | Page: | 2 |

| Project: | RUWAIS SULPHUR GRANULATION PLANT AT RSHT - 2 FOR HAIL & GHASHA PROJECT (1005312) |
| --- | --- |
| Subject: | CONFIRMATION OF COST BEARING AND SET-OFF FOR PERSONNEL SECONDED FROM CCECC |

Dear Mr. Zhang Gang,

The Subcontractor and the Contractor entered into the Subcontract for the Civil Works of Package I & III on 22 Nov 2025 (Subcontract No. WISON24108C25007, hereinafter referred to as the “Subcontract”).
分包商与承包商就土建工程 Package I & III 于 2025 年 11 月 22 日签订《分包合同》（编号 WISON24108C25007，以下简称“《分包合同》”）。

Due to the serious delay in the progress of the buildings undertaken by the Subcontractor, including the Substation, Local Control Room and Operation Shelter, and the slow mobilization of manpower, pursuant to Sub-Clause 10.11 (Recovery) of the Subcontract and Item 21 of the Clarification Form of LOA (Appendix 4), the Contractor is entitled to provide additional resources to expedite the Works, and all costs incurred therefrom shall be borne by the Subcontractor.
因分包商承担的变电站、就地控制室、操作间等建筑物进度严重滞后，且人力动员缓慢，依据《分包合同》Sub-Clause 10.11（进度恢复）及 LOA的Clarification Form（Appendix 4）第 21 项，承包商有权提供额外资源以加速工程，且发生的全部成本由分包商承担。

As agreed, the Contractor has arranged for personnel to be seconded from CCECC to supplement the Subcontractor's construction site and be placed under the unified management of the Subcontractor, and the costs arising therefrom shall be deducted from the Subcontractor's interim payments pursuant to Article 11 “Set-off” of the Subcontract.
经协商，承包商安排由 CCECC 借调人员补充至分包商施工现场、纳入分包商统一管理，由此产生的费用按 Article 11 从分包商进度款中扣付。

CCECC has claimed the aforesaid costs from the Contractor through its letter ref. SLT-5312-CCE-WSN-0050 (see Enclosure), setting out the breakdown of the manpower unit rates and the timesheets confirmed by the three Parties up to 3 Sep 2026.
CCECC 已通过其 SLT-5312-CCE-WSN-0050 号函（见附件）向承包商主张上述费用，并列明了人力单价各要素构成及截止 2026 年 9 月 3 日三方确认的工时单。

Accordingly, the Contractor hereby confirms the bearing and settlement mechanism of the aforesaid costs as follows:
据此，承包商现就上述费用的承担及结算机制安排如下：

(1) The Subcontractor may either pay the aforesaid costs directly to CCECC, or entrust the Contractor to make the payment on its behalf, in which case the Contractor shall deduct the amount from any interim payment or any other sums due to the Subcontractor pursuant to Article 11 “Set-off” of the Subcontract;
上述费用分包商可直接支付给 CCECC，或委托承包商支付并由承包商依据《分包合同》Article 11 从分包商任何一期进度款或应付款项中扣除；

(2) Where the Subcontractor entrusts the Contractor to make the payment, the subsequent costs of the seconded personnel shall be summarized periodically or from time to time under the same mechanism and deducted from the Subcontractor’s interim payments for onward payment, without the need for a separate letter of confirmation on each occasion;
如分包商委托承包商支付，则后续发生的借调用工，将按同一机制定期或不定期汇总，并从分包商进度款中扣除转付，不再逐批另行发函要求确认；

(3) All timesheets signed by the three Parties shall be the sole source and basis for each deduction.
所有经三方签字的用工表，将作为各次扣款费用的唯一来源和依据。

The Subcontractor is requested to confirm in writing, within seven (7) calendar days from the date of this letter, the manpower unit rates (with element breakdown) attached to the letter ref. SLT-5312-CCE-WSN-0050 and the working hours incurred to date. The issuance or performance of this letter is without prejudice to, and shall not be deemed a waiver of, any rights and remedies of the Contractor under the Subcontract and applicable law.
请分包商于本函发出之日起七（7）个日历日内，对 SLT-5312-CCE-WSN-0050 号函所附的人力单价（各要素构成）及目前已发生的工时予以书面确认。本函的发出或履行不影响且不视为放弃承包商依据《分包合同》及适用法律所享有的一切权利与救济。

Sincerely yours,

Feng Guoling

CONTRACTOR’s Representative

Wison Energy Engineering (Hong Kong) Limited - Abu Dhabi

CC: N/A

Enclosure: CCECC letter ref. SLT-5312-CCE-WSN-0050 and all its attachments.